## Example Wall 4.0 m
|  | Kalk-Row: | A | B | C | D | E | F | G | H | J | K | L | M | N | O |  | P | Q | R | S | T | U
[7 empty] | 1. Billing cycle | [10 empty] | 2. Billing cycle
Basic data | [6 empty] | Cost Types with out supplement per unit |  |  |  |  | Cost Types with out supplement Total | [5 empty] | Cost Types with supplement Total |  |  |  | Unit-price | Total-price |  | list of bid items and quantities
Row | Bill of quantities Nr. | Kalk.-Nr. / Short text | Quantity | Unit | Aufwand (Lohn-hr) | Capacity | Wage-Cost | Other-Costs | Equipment-costs | External-costs | Sum Wage-hr | Wage-Cost | Other-Costs | Equipment-costs | External-costs | Kontroll- Summe direct costs |  | Wage-Cost | Other-Costs | Equipment-costs | External-costs
|  |  |  | [Unit] | [hr/Unit] | [Unit/hr] | [€/Unit] | [€/Unit] | [€/Unit] | [€/Unit] | [hr] | [€] | [€] | [€] | [€] | [€] |  | [€] | [€] | [€] | [€] | [€/Unit] | [€]
1 | 1 | Noise and view protection wall | 300 | m | [17 empty] | 1078.7263 | 323617.8769
2 | 1.4 | Excavation | 769.5 | m3 | 0.23311 | 8.5796 | 1.4569 | 0.34617 | 2.1501 | 1e-08 | 179.3782 | 1121.1139 | 266.3767 | 1654.4844 | 7.695e-06 | 3041.975 |  | 5572.368 | 452.8403 | 2150.8298 | 8.8493e-06 | 10.6251 | 8176.038 |  | Pos. 1.4
3 | zu 1.3 | Blinding | 600 | m2 | 0.1244 | 16.0767 | 0.77752 | 6.7 | 1e-08 | 1e-08 | 74.642 | 466.5127 | 4020 | 6e-06 | 6e-06 | 4486.5127 |  | 2318.7477 | 6834 | 7.8e-06 | 6.9e-06 | 15.2546 | 9152.7477 |  | Pos. 1.3
4 | 1.3 | Reinforced concrete foundation | 270 | m3 | 0.66746 | 2.9964 | 18.7276 | 175.6133 | 1e-07 | 1e-07 | 180.2153 | 5056.4512 | 47415.6 | 2.7e-05 | 2.7e-05 | 52472.0513 |  | 25132.5107 | 80606.52 | 3.51e-05 | 3.105e-05 | 391.626 | 105739.0308 |  | Pos. 1.3
5 | 1.2 | Prefabricated reinforced concrete columns | 101 | Stk | 8 | 0.25 | 50 | 213.5127 | 111.6117 | 1e-08 | 808 | 5050 | 21564.7875 | 11272.7867 | 1.01e-06 | 37887.5743 |  | 25100.4457 | 36660.1387 | 14654.6228 | 1.1615e-06 | 756.5862 | 76415.2072 |  | Pos. 1.2
6 | 1.1 | Brick masonry | 1040 | m2 | 1.0266 | 1.9483 | 6.416 | 24.5 | 1e-07 | 1e-07 | 1067.6206 | 6672.6289 | 25480 | 0.000104 | 0.000104 | 32152.6291 |  | 33165.5365 | 43316 | 0.0001352 | 0.0001196 | 73.5399 | 76481.5368 |  | Pos. 1.1
7 | zu 1.4 | Backfill | 439.5 | m3 | 0.15479 | 12.921 | 0.96742 | 1e-07 | 1e-07 | 1e-07 | 68.029 | 425.1813 | 4.395e-05 | 4.395e-05 | 4.395e-05 | 425.1814 |  | 2113.3149 | 7.4715e-05 | 5.7135e-05 | 5.0542e-05 | 4.8085 | 2113.3151 |  | Pos. 1.4
8 | 1.5 | Steel construction | 24 | ton | --- | --- | 1e-05 | 1e-07 | 1e-07 | 1650 | 0.001 | 0.00024 | 2.4e-06 | 2.4e-06 | 39600 | 39600.0002 |  | 0.0011929 | 4.08e-06 | 3.12e-06 | 45540 | 1897.5001 | 45540.0012 |  | Pos. 1.5
9 | [17 empty] | 0 | 0 | 0 | 0
10 | --- | Wages [€/hr] | 25 | [7 empty] | Sum direct costs: | 18791.8882 | 98746.7642 | 12927.2714 | 39600.0002 | 170065.924 |  | 93402.9248 | 167869.4991 | 16805.4528 | 45540.0002 | Kontrolle: | 323617.8769 | = | BS(2)
11 | --- | Sum Direct costs-Wage hours: | 2377.8862 | [7 empty] | Sum On-Site overhead: | 46254.4717 | 2918.1572 | 46128.1062 | 1e-05 | 95300.7351 | = | on-site overhead |  | Kontrolle: | 323617.8769
12 | --- | Sum On site overhead-Wage hours | 1500 | [7 empty] | Sum Production costs: | 65046.3599 | 101664.9214 | 59055.3775 | 39600.0002 | 265366.6591 | = | Production costs
13 | --- | Sum Production Costs-Wage hours | 3877.8862 | [11 empty] | Indirect Costs | 37216.0558 |  | Wage-Cost | Other-Costs | Equipment-costs | External-costs
14 | --- | Construction time in Weeks: | 12 | [11 empty] | Risk & Profit | 21035.162 |  | 397% | 70% | 30% | 15% | Apportionment in [%]
15 | --- | Average Labour (40 hr/Week): | 8.0789 | [11 empty] | Apportionment of indirect costs: | 153551.9529 | = | 74611.0365 | 69122.7349 | 3878.1814 | 5940 | Apportionment absolut in [$]
16 | --- | Total Indirect costs: | 11.5% | [11 empty] | Total production cost (SK): | 302582.7149 |  |  |  | Kontrolle: | 153551.9529
17 | --- | Risk and Profit: | 6.5% | [11 empty] | Bid Sum (netto): | 323617.8769 | = | BS(1)
18 | --- | Tax rate: | 19% | [11 empty] | Bid Sum (brutto): | 385105.2735
Probability
|  |  | Scenario's confidence interval 10% Optimistic 45% Expected 90% Pessimistic |  |  |  |  | Scenarios |  |  | Contingency |  |  |  |  | 100%
[8 empty] | Optimistic (10%) |  |  | 0
385105.2735
Expected (45%)
[8 empty] | 385105.2735 |  |  | Contingency %
[8 empty] | Pessimistic (90%) |  |  | 0%
385105.2735

## RiskSerializationData (hidden)
3 | 0
0
25.2823 | TRUE | 0 | 1 | GF1_rK0qDwEACADNAAwjACYAOABcAGUAZgByAH4AqwApAMcALQD//wAAAAABAQEAAQQAAAAAATAAAAABHkR1cmF0aW9uIC8gQ29uY3JldGUgRm91bmRhdGlvbgEAAQEFAAEAAQMBAQD/AQEBAQEAAQEBAAIAAQEBAQEAAQEBAAIAAYIAAiUAHkR1cmF0aW9uIC8gQ29uY3JldGUgRm91bmRhdGlvbgAALwECAAIAswC9AAEBAgGamZmZmZmpPwAAZmZmZmZm7j8AAAUAAQEBAA== | 1 | 0 | 0 | >75% | <25% | >90% | 25.2823 | 42 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
35.2823 | TRUE | 0 | 1 | GF1_rK0qDwEACADIAAwjACYAOABaAGMAZABwAHwApwApAMIALQD//wAAAAABAQEAAQQAAAAAATAAAAABHENvbmNyZXRlIGZvdW5kYXRpb24gU2NoZWR1bGUBAAEBBQABAAEDAQEA/wEBAQEBAAEBAQACAAEBAQEBAAEBAQACAAGAAAIjABxDb25jcmV0ZSBmb3VuZGF0aW9uIFNjaGVkdWxlAAAvAQIAAgCvALgAAQECAQAAAAAAAPD/AWZmZmZmZu4/AAAFAAEBAQA= | 1 | 0 | 0 | >75% | <25% | >90% | 35.2823 | 44 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
58.3631 | TRUE | 0 | 1 | GF1_rK0qDwEACAC/AAwjACYAOABVAF4AXwBrAHcAnQApALkALQD//wAAAAABAQEAAQQAAAAAATAAAAABF0NsZWFyIHRoZSBzaXRlIFNjaGVkdWxlAQABAQUAAQABAwEBAP8BAQEBAQABAQEAAgABAQEBAQABAQEAAgABewACHgAXQ2xlYXIgdGhlIHNpdGUgU2NoZWR1bGUAAC8BAgACAKUArwABAQIBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQA= | 1 | 0 | 0 | >75% | <25% | >90% | 58.3631 | 49 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 14000 | 6709375 | 36400 | 100
FALSE | 14000 | 6709375 | 36400 | 500
FALSE | 14000 | 6709375 | 36400 | 1000
FALSE | 14000 | 6709375 | 36400 | 1500
FALSE | 14000 | 6709375 | 36400 | 2000
0

## Schedule
Nr. | 0 | Duration | 0 | Nr. |  | Duration
Start |  |  |  | Beschreibung
0 | 0 | 0 | 0 | FAZ | GP | FP | FEZ
0 |  |  | 0 | SAZ |  |  | SEZ
Nr. | 0 | Duration | 3 | Nr. | 0 | Duration | 5.6056 |  |  | Nr. | 0 | Duration | 2.1259
BE |  |  |  | Excavation | [5 empty] | Backfill Foundation
0 | 0 | 0 | 3 | 4 | 0 | 0 | 9.6056 |  |  | 35.2823 | 0 | 0 | 37.4082
0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | Nr. | 0 | Duration | 25.2823 |  |  | Nr. | 0 | Duration | 3
[6 empty] | Concrete foundation | [5 empty] | Rework
[6 empty] | 10 | 0 | 0 | 35.2823 |  |  | 41.25 | 0 | 0 | 44.25
Simulation | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
Optimistic (10%)
58.3631
expectedic (45%) | [7 empty] | Nr. | 0 | Duration | 25.25 |  |  | Nr. | 0 | Duration | 3
58.3631 | [7 empty] | Prefabricated columns | [5 empty] | clear the site
Pesimistic (90%) | [7 empty] | 19 | 0 | 0 | 44.25 |  |  | 55.3631 | 0 | 0 | 58.3631
58.3631 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | Nr. | 0 | Duration | 33.3631 |  |  | Nr. | 0 | Duration | 0
[10 empty] | Brick masonry | [5 empty] | Ende
[10 empty] | 22 | 0 | 0 | 55.3631 |  |  | 58.3631 | 0 | 0 | 58.3631
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[16 empty] | Probability |  |  | 100%
[16 empty] | Expected |  |  | 58.3631

## Calculations
Activity | Quantity | Unit | Performance | Unit | Performance factor | Unit | Duration (hr) | Crew | Duration (Man-hr) | Duration (day) | Expected (45%)
Excavation | 769.5 | m³ | 8.5796 | m³/hr | 0.23311 | Man-hr/m³ | 89.6891 | 2 | 44.8446 | 5.6056 | 5.6056
Blinding lean concrete | 60 | m³
bzw. | 600 | m² | 16.0767 | m²/hr | 0.1244 | Man-hr/m² | 37.321 | 2 | 18.6605 | 2.3326 | 2.3326
Formwork(Foundation) | 391.95 | m²
Concrete (Foundation) | 270 | m³ | 0.66746 | m³/hr | 2.9964 | Man-hr/m³ | 404.5161 | 2 | 202.258 | 25.2823 | 25.2823
Steel (Foundation) | 21.6 | ton
Concrete Columns | 101 | Piece | 0.25 | Piece /hr | 8 | Man-hr/Piece | 404 | 2 | 202 | 25.25 | 25.25
Brick masonry | 1040 | m² | 1.9483 | m²/hr | 1.0266 | Man-hr/m² | 533.8103 | 2 | 266.9052 | 33.3631 | 33.3631
Backfill | 439.5 | m³ | 12.921 | m³/hr | 0.15479 | Man-hr/m³ | 34.0145 | 2 | 17.0073 | 2.1259 | 2.1259
Equipment Costs | [7 empty] | Direct Costs | [14 empty] | Direct Costs Overview
Backhoe-loader |  |  |  | Rough-Terrain-Crane |  |  |  | Excavation | [7 empty] | Reinforced Concrete Foundation | [6 empty] | Excavation |  |  |  | Brick masonry
K | = a + v bzw. a + z |  |  | A+V | mean | 4350 |  | Wage | Duration | Unit | Costs | Unit | Total | Unit |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
a | 2.8571 | % |  | BGL | minimum | 4130 |  |  | 44.8446 | Man-hr | 25 | €/Man-hr | 1121.1139 | € |  |  | 202.258 | Man-hr | 25 | €/Man-hr | 5056.4512 | € | Wage | 1121.1139 | 769.5 | 1.4569 | Wage | 6672.6289 | 1040 | 6.416
v | 35 | mon |  |  | mean | 4350 |  | Costs. Inv. | Materials | Unit | Engine power | Unit | Diesel | Unit | Total | Costs. Inv. | Quantity | Unit | Costs-Fw. | Unit | Total | Unit | Costs. Inv. | 266.3767 | 769.5 | 0.34617 | Costs. Inv. | 25480 | 1040 | 24.5
n | 4 |  |  |  | maximum | 4570 |  |  | 0.12 | l/(Kw*Std) | 60 | KW | 1.1 | €/L | 7.92 | Fromwork | 391.95 | m³ | 8 | €/Man-hr | 3135.6 | € | Equipment | 1654.4844 | 769.5 | 2.1501 | Equipment
zinz | 6.5 | % |  |  | per Tag | 217.5 |  |  | 0.1 | minimum |  |  | 1 | minimum |  |  |  |  | 7 | minimum |  |  | Sub. Cont. |  |  |  | Sub. Cont.
v | 0.37143 | % |  | Rep BGL | 2830 | €/Month |  |  | 0.12 | mean |  |  | 1.1 | mean |  |  |  |  | 8 | mean |  |  | Total | 3041.975 |  | 3.9532 | Total | 32152.6289 |  | 30.916
a+v = k | 3.2286 | % |  | Rep Wage | 1698 | €/Month |  |  | 0.15 | maximum |  |  | 1.3 | maximum |  |  |  |  | 10 | maximum |  |  | Probability |  | 100% |  | Probability |  | 100%
NW | 77700 | € |  | Rep Wage SZ | 1748.94 | €/Month |  |  | Total | Unit | hr/day | Workload | Duration (day) | Total | Unit | Total | Quantity | Unit | Costs-Rf.-C. | Unit | Total | Unit | mean (45%) |  | 3041.975 |  | mean (45%) |  | 32152.6289
A+V | 2508.6 | € |  | SZ (%) | mean | 103 |  |  | 7.92 | € | 8 | 75% | 5.6056 | 266.3767 | € | Reinforcement | 21.6 | ton | 800 | €/ton | 17280 | $
Per day | 125.43 | €/day |  | SZ (%) | minimum | 101 | [5 empty] | 65% | minimum | [5 empty] | 750 | minimum |  |  | Blinding/lean concrete |  |  |  | Backfill
Per hour | 15.6787 | €/hr |  |  | mean | 103 | [5 empty] | 75% | mean | [5 empty] | 800 | mean |  |  | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
reffektiv | 4.3686 | % |  |  | maximum | 109 | [5 empty] | 85% | maximum | [5 empty] | 1100 | maximum |  |  | Wage | 466.5127 | 600 | 0.77752 | Wage | 425.1813 | 439.5 | 0.96742
rBGL (%) |  | 2.7 |  | Rep total | 4578.94 | €/Month |  | Equipment | A+V | Unit | Repair | Unit | Duration (day) | Unit | Total | Total | Quantity | Unit | Costs-Conc. | Unit | Total | Unit | Costs. Inv. | 4020 | 600 | 6.7 | Costs. Inv.
| minimum | 2.3 |  | per Tag | 228.947 | €/day |  |  | 125.43 | €/day | 169.7201 | €/At | 5.6056 | Tag | 1654.4844 | Concrete | 270 | m³ | 100 | €/m³ | 27000 | $ | Equipment |  |  |  | Equipment
| mean | 2.7 |  | A+V+Rep | 8928.94 | €/Month |  | Total Excavation | [6 empty] | 3041.975 |  |  |  | 90 | minimum |  |  | Sub. Cont. |  |  |  | Sub. Cont.
| maximum | 4.5 |  | per Tag | 446.447 | €/day | [12 empty] | 100 | mean |  |  | Total | 4486.5127 |  | 7.4775 | Total | 425.1813 |  | 0.96742
SZ | 103 | % | [5 empty] | Blinding | [10 empty] | 115 | maximum |  |  | Probability |  | 100% |  | Probability |  | 100%
R | 3394.4022 | €/Month |  | zu verrechnen |  |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit |  | Total Costs. Inv. | [5 empty] | 47415.6 | mean (45%) |  | 4486.5127 |  | mean (45%) |  | 425.1813
Per Day | 169.7201 | €/day |  | Duration (day) | Costs (€/AT) | Total (€) |  |  | 18.6605 | Man-hr | 25 | €/Man-hr | 466.5127 | € |  | Total Reinforced Concrete Foundation | [5 empty] | 52472.0512
Per Hour | 21.215 | €/hr |  | 27 | 446.447 | 12054.069 |  | Costs. Inv. | Quantity | Unit | Costs | Unit | Total | Unit | [8 empty] | Reinforced Concrete Foundation |  |  |  | Steel structure
A+V+Rep | 5903.0022 | €/Month |  |  | $ per Piece | 119.3472 |  |  | 60 | m³ | 67 | €/Man-hr | 4020 | € |  | Brick masonry | [6 empty] | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
per Tag | 295.1501 | €/day | [8 empty] | 65 | minimum |  |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | Wage | 5056.4512 | 270 | 18.7276 | Wage
[11 empty] | 67 | mean |  |  |  |  | 266.9052 | Man-hr | 25 | €/Man-hr | 6672.6289 | € | Costs. Inv. | 47415.6 | 270 | 175.6133 | Costs. Inv.
to settle |  |  |  | Wage | [6 empty] | 72 | maximum |  |  |  | Costs. Inv. | Quantity | Unit | Waste | Costs-masonry | Unit | Total | Equipment |  |  |  | Equipment
Duration (Day) | Costs (€/Day) | Total (€) |  | 25 | €/Man-hr |  |  | Total Blinding/lean concrete | [6 empty] | 4486.5127 | Brick masonry | 1040 | m² | 7.5% | 20 | €/Man-hr | 22360 | Sub. Cont. |  |  |  | Sub. Cont. | 39600 | 24 | 1650
8 | 295.1501 | 2361.2009 | [15 empty] | minimum | 5% | 18 | minimum |  | Total | 52472.0512 |  | 194.3409 | Total | 39600 |  | 1650
| $ per m³ | 3.0685 | [5 empty] | Prefabricated Columns | [9 empty] | mean | 7.5% | 20 | mean |  | Probability |  | 100% |  | Probability |  | 100%
[8 empty] | Wage | Duration | Unit | Costs | Unit | Total | Unit |  |  |  | maximum | 10% | 22 | maximum |  | mean (45%) |  | 52472.0512 |  | mean (45%) |  | 39600
[9 empty] | 202 | Man-hr | 25 | €/Man-hr | 5050 | € |  |  | Quantity | Costs-Mort. | Unit | Costs | Unit | Total
[8 empty] | Costs. Inv. | Materials | Unit | Engine power | Unit | Diesel | Unit | Total | Mortar (m³) | 1040 | 0.1 | €/L | 30 | €/m² | 3120 | Prefabricated Columns
[9 empty] | 0.15 | l/(Kw*Std) | 85 | KW | 1.1 | €/L | 14.025 |  |  | 0.08 | minimum | 25 | minimum |  | Cost types | € | Quantity | €/Unit
[9 empty] | 0.13 | minimum |  |  | 1 | minimum |  |  |  | 0.1 | mean | 30 | mean |  | Wage | 5050 | 101 | 50
[9 empty] | 0.15 | mean |  |  | 1.1 | mean |  |  |  | 0.12 | maximum | 35 | maximum |  | Costs. Inv. | 21564.7875 | 101 | 213.5127
[9 empty] | 0.2 | maximum |  |  | 1.3 | maximum |  | Total Costs. Inv. | [5 empty] | 25480 | Equipment | 11272.7867 | 101 | 111.6117
[9 empty] | Total | Unit | hr/day | Workload | Duration (day) | Total | Unit | Total Brick masonry | [5 empty] | 32152.6289 | Sub. Cont.
[9 empty] | 14.025 | € | 8 | 75% | 25.25 | 2124.7875 | € | [7 empty] | Total | 37887.5742 |  | 375.1245
[12 empty] | 65% | minimum |  |  | Backfill | [6 empty] | Probability |  | 100%
[12 empty] | 75% | mean |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | mean (45%) |  | 37887.5742
[12 empty] | 85% | maximum |  |  |  | 17.0073 | Man-hr | 25 | €/Man-hr | 425.1813 | €
[9 empty] | Columns | Quantity | Unit | Costs-Columns | Unit | Total | Unit
[10 empty] | 81 | Piece | 240 | €/Piece | 19440 | € | Steel structure
[12 empty] | 220 | minimum | Costs. Inv. |  | Sub. Cont. | Quantity | Unit | Costs | Unit | Total | Unit
[12 empty] | 240 | mean | 21564.7875 |  |  | 24 | ton | 1650 | €/ton | 39600 | €
[12 empty] | 260 | maximum
[8 empty] | Equipment | A+V | Unit | Repair | Unit | Duration (day) | Unit | Total
[9 empty] | 217.5 | €/day | 228.947 | €/day | 25.25 | Tag | 11272.7867
[8 empty] | Total Aushub | [6 empty] | 37887.5742
Indirect Costs
| Duration | Unit | Costs | Unit | hr/day | Workload | total
Wage hours | 1500 | Std | 25 | €/hr |  |  | 37500
Supervision | 2.9182 | Mo | 3000 | €/Mo |  |  | 8754.4717
Additional Equipment | 2.9182 | Mo | 3500 | €/Mo |  |  | 10213.5503
Backhoe-loader | 52.7576 | day | 295.1501 | €/day |  |  | 15571.4041
| 58.3631 | day | 7.92 | €/hr | 8 | 75% | 2773.4166
Mobile Crane | 33.1131 | day | 446.447 | €/day |  |  | 14783.264
| 33.1131 | day | 14.025 | €/hr | 8 | 75% | 2786.4711
Miscellaneous | 2.9182 | Mo | 1000 | €/Mo |  |  | 2918.1572
95300.7351

## Inputs
Considerations to Performance factor |  |  |  |  | Perf. (Wage-hr) | Capacity | Simulation |  |  | NN-Prediction
Aktivität | [6 empty] | Performance |  |  | Activity | [hr/Unit] | Crew | [Unit/hr]
| Performance | Unit | Crew | Unit | [hr/Unit] | [Unit/hr] | Optimistic | Expected | Pessimistic | Excavation | 0.23311 | 2 | 8.5796
Excavation: | 8.5796 | m³/hr | 2 | Man | 0.23311 | 8.5796 | 8.5796 | 8.5796 | 8.5796 | Blinding | 0.1244 | 2 | 16.0767
minimum | 8.408 |  | 1 | minimum |  |  | Crew |  |  | Reinforced Concrete | 0.66746 | 2 | 2.9964
expected | 8.5796 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic | Prefabricated Columns | 8 | 2 | 0.25
maximum | 8.7512 |  | 2 | maximum |  |  | 2 | 2 | 2 | Brick masonry | 1.0266 | 2 | 1.9483
[7 empty] | Aufwand |  |  | Backfill | 0.15479 | 2 | 12.921
[7 empty] | Optimistic | Expected | Pessimistic
Blinding: | 16.0767 | m²/hr | 2 | Mann (LW) | 0.1244 | 16.0767 | 16.0767 | 16.0767 | 16.0767
minimum | 15.7552 |  | 1 | minimum |  |  | Crew
expected | 16.0767 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 16.3983 |  | 2 | maximum |  |  | 2 | 2 | 2
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Reinforced concrete: | 2.9964 | Mann-hr/m³ | 2 | Mann (AW) | 0.66746 | 2.9964 | 2.9964 | 2.9964 | 2.9964
minimum | 2.9365 |  | 1 | minimum |  |  | Crew
expected | 2.9964 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 3.0563 |  | 2 | maximum |  |  | 2 | 2 | 2
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Prefabricated reinforced concrete columns: | 8 | Mann-hr/Stk | 2 | Mann (AW) | 8 | 0.25 | 8 | 8 | 8
minimum | 6 |  | 1 | minimum |  |  | Crew
expected | 8 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 10 |  | 2 | maximum |  |  | 2 | 2 | 2
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Brick masonry: | 1.0266 | Mann-hr/m² | 2 | Mann (AW) | 1.0266 | 1.9483 | 1.0266 | 1.0266 | 1.0266
minimum | 1.006 |  | 1 | minimum |  |  | Crew
expected | 1.0266 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 1.0471 |  | 2 | maximum |  |  | 2 | 2 | 2
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Backfill: | 12.921 | m³/hr | 2 | Mann (LW) | 0.15479 | 12.921 | 12.921 | 12.921 | 12.921
minimum | 12.6625 |  | 1 | minimum |  |  | Crew
expected | 12.921 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 13.1794 |  | 2 | maximum |  |  | 2 | 2 | 2

## NN-Predictions
Excavation Numeric | Tag Used | Prediction | Target | Variation
| predict | 0.23311 | 0.23166 | 0.626%
| predict | 0.3207 | 0.32416 | -1.066%
Excavation Text | Tag Used | Prediction | Target | Variation
| predict | 0.29863 | 0.23166 | 28.91%
| predict | 0.30593 | 0.32416 | -5.623%
Blinding Numeric | Tag Used | Prediction | Target | Variation
| predict | 0.12428 | 0.12393 | 0.2804%
| predict | 0.098942 | 0.09792 | 1.044%
Blinding Text | Tag Used | Prediction | Target | Variation
| predict | 0.1244 | 0.12393 | 0.382%
| predict | 0.097958 | 0.09792 | 0.03885%
Reinforced Concrete Numeric | Tag Used | Prediction | Target | Variation
| predict | 0.66781 | 0.66825 | -0.06656%
| predict | 1.5901 | 1.59 | 0.007194%
Reinforced Concrete Text | Tag Used | Prediction | Target | Variation
| predict | 0.66746 | 0.66825 | -0.1176%
| predict | 1.5638 | 1.59 | -1.646%
Masonry Numeric | Tag Used | Prediction | Target | Variation
| predict | 1.0214 | 1.0296 | -0.7965%
| predict | 0.66994 | 0.6669 | 0.4554%
Masonry Text | Tag Used | Prediction | Target | Variation
| predict | 1.0266 | 1.0296 | -0.2954%
| predict | 0.60287 | 0.6669 | -9.601%
Backfil Numeric |  | Prediction | Target | Variation
| predict | 0.10278 | 0.10098 | 1.787%
| predict | 0.15479 | 0.15593 | -0.7297%
Backfil Text | Tag Used | Prediction | Target | Variation
| predict | 0.10277 | 0.10098 | 1.777%
| predict | 0.15472 | 0.15593 | -0.7745%
Note on D2: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Site conditions Equipment Weather Factor
Note on D5: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Site conditions Equipment Weather Independent Numeric Variables: 1 Factor
Note on D9: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Cement Conditions Weather Factor
Note on D12: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Cement Conditions Weather Independent Numeric Variables: 1 Factor
Note on D16: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Concrete Conditions Producer Factor
Note on D19: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Concrete Conditions Producer Independent Numeric Variables: 1 Factor
Note on D23: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Site conditions Equipment Weather Factor
Note on D26: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Site conditions Equipment Weather Independent Numeric Variables: 1 Factor
Note on D30: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Site conditions Equipment Weather Factor
Note on D33: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Site conditions Equipment Weather Independent Numeric Variables: 1 Factor

## Analysis
Alt.- 4.0 m
Criteria | Duration (d) | Expected (45 %) | Difference
Total Duration | 58.3631 | 58.3631 | 0
Excavation | 5.6056 | 5.6056 | 0
Blinding lean concrete | 2.3326 | 2.3326 | 0
Concrete (Foundation) | 25.2823 | 25.2823 | 0
Concrete Columns | 25.25 | 25.25 | 0
Brick masonry | 33.3631 | 33.3631 | 0
Backfill | 2.1259 | 2.1259 | 0
Costs | Unit
Bid Sum (brutto): | 385105.2735
Contingency (Expected Scenario) | 0
Optimistic Scenario | 385105.2735
Expected Scenario | 385105.2735
Pessimistic Scenario | 385105.2735
Direct Costs | Expected (45%) | Probability
Excavation | 3041.975 | 100%
Bliding | 4486.5127 | 100%
Prefabricated Columns | 37887.5742 | 100%
Reinforced Conrete Foundation | 52472.0512 | 100%
Brick Masonry | 32152.6289 | 100%
Backfilling | 425.1813 | 100%