## Example Wall 5.0 m
|  | Kalk-Row: | A | B | C | D | E | F | G | H | J | K | L | M | N | O |  | P | Q | R | S | T | U
[7 empty] | 1. Billing cycle | [10 empty] | 2. Billing cycle
Basic data | [6 empty] | Cost Types with out supplement per unit |  |  |  |  | Cost Types with out supplement Total | [5 empty] | Cost Types with supplement Total |  |  |  | Unit-price | Total-price |  | list of bid items and quantities
Row | Bill of quantities Nr. | Kalk.-Nr. / Short text | Quantity | Unit | Aufwand (Lohn-hr) | Capacity | Wage-Cost | Other-Costs | Equipment-costs | External-costs | Sum Wage-hr | Wage-Cost | Other-Costs | Equipment-costs | External-costs | Kontroll- Summe direct costs |  | Wage-Cost | Other-Costs | Equipment-costs | External-costs
|  |  |  | [Unit] | [hr/Unit] | [Unit/hr] | [€/Unit] | [€/Unit] | [€/Unit] | [€/Unit] | [hr] | [€] | [€] | [€] | [€] | [€] |  | [€] | [€] | [€] | [€] | [€/Unit] | [€]
1 | 1 | Noise and view protection wall | 300 | m | [17 empty] | 982.0025 | 294600.7571
2 | 1.4 | Excavation | 937.5 | m3 | 0.23311 | 8.5796 | 1.4569 | 0.34617 | 2.1501 | 1e-08 | 218.5407 | 1365.8795 | 324.533 | 2015.6974 | 9.375e-06 | 3706.1099 |  | 6640.4045 | 551.706 | 2620.4066 | 1.0781e-05 | 10.4667 | 9812.5172 |  | Pos. 1.4
3 | zu 1.3 | Blinding | 600 | m2 | 0.1244 | 16.0767 | 0.77752 | 6.7 | 1e-08 | 1e-08 | 74.642 | 466.5127 | 4020 | 6e-06 | 6e-06 | 4486.5127 |  | 2268.0133 | 6834 | 7.8e-06 | 6.9e-06 | 15.17 | 9102.0133 |  | Pos. 1.3
4 | 1.3 | Reinforced concrete foundation | 367.5 | m3 | 0.66746 | 5.9928 | 9.3638 | 173.8531 | 1e-07 | 1e-07 | 245.2931 | 3441.196 | 63891 | 3.675e-05 | 3.675e-05 | 67332.196 |  | 16729.8312 | 108614.7 | 4.7775e-05 | 4.2262e-05 | 341.0736 | 125344.5313 |  | Pos. 1.3
5 | 1.2 | Prefabricated reinforced concrete columns | 101 | Stk | 8 | 0.5 | 12.5 | 197.7346 | 27.9029 | 1e-08 | 808 | 1262.5 | 19971.1969 | 2818.1967 | 1.01e-06 | 24051.8936 |  | 6137.8114 | 33951.0347 | 3663.6557 | 1.1615e-06 | 433.1931 | 43752.5018 |  | Pos. 1.2
6 | 1.1 | Brick masonry | 1300 | m2 | 1.0266 | 5.8448 | 0.71289 | 24.5 | 1e-07 | 1e-07 | 1334.5258 | 926.754 | 31850 | 0.00013 | 0.00013 | 32776.7543 |  | 4505.5377 | 54145 | 0.000169 | 0.0001495 | 45.1158 | 58650.538 |  | Pos. 1.1
7 | zu 1.4 | Backfill | 510 | m3 | 0.15479 | 12.921 | 0.96742 | 1e-07 | 1e-07 | 1e-07 | 78.9415 | 493.3845 | 5.1e-05 | 5.1e-05 | 5.1e-05 | 493.3846 |  | 2398.6541 | 8.67e-05 | 6.63e-05 | 5.865e-05 | 4.7032 | 2398.6543 |  | Pos. 1.4
8 | 1.5 | Steel construction | 24 | ton | --- | --- | 1e-05 | 1e-07 | 1e-07 | 1650 | 0.001 | 0.00024 | 2.4e-06 | 2.4e-06 | 39600 | 39600.0002 |  | 0.0011668 | 4.08e-06 | 3.12e-06 | 45540 | 1897.5 | 45540.0012 |  | Pos. 1.5
9 | [17 empty] | 0 | 0 | 0 | 0
10 | --- | Wages [€/hr] | 25 | [7 empty] | Sum direct costs: | 7956.2268 | 120056.7299 | 4833.8943 | 39600.0002 | 172446.8513 |  | 38680.2534 | 204096.4408 | 6284.0626 | 45540.0003 | Kontrolle: | 294600.7571 | = | BS(2)
11 | --- | Sum Direct costs-Wage hours: | 2759.9441 | [7 empty] | Sum On-Site overhead: | 41945.0655 | 1481.6885 | 25699.0155 | 1e-05 | 69125.7696 | = | on-site overhead |  | Kontrolle: | 294600.7571
12 | --- | Sum On site overhead-Wage hours | 1500 | [7 empty] | Sum Production costs: | 49901.2924 | 121538.4184 | 30532.9099 | 39600.0002 | 241572.6209 | = | Production costs
13 | --- | Sum Production Costs-Wage hours | 4259.9441 | [11 empty] | Indirect Costs | 33879.0871 |  | Wage-Cost | Other-Costs | Equipment-costs | External-costs
14 | --- | Construction time in Weeks: | 12 | [11 empty] | Risk & Profit | 19149.0492 |  | 386.2% | 70% | 30% | 15% | Apportionment in [%]
15 | --- | Average Labour (40 hr/Week): | 8.8749 | [11 empty] | Apportionment of indirect costs: | 122153.9059 | = | 30724.0266 | 84039.7109 | 1450.1683 | 5940 | Apportionment absolut in [$]
16 | --- | Total Indirect costs: | 11.5% | [11 empty] | Total production cost (SK): | 275451.7079 |  |  |  | Kontrolle: | 122153.9059
17 | --- | Risk and Profit: | 6.5% | [11 empty] | Bid Sum (netto): | 294600.7571 | = | BS(1)
18 | --- | Tax rate: | 19% | [11 empty] | Bid Sum (brutto): | 350574.901
Probability
|  |  | Scenario's confidence interval 10% Optimistic 45% Expected 90% Pessimistic |  |  |  |  | Scenarios |  |  | Contingency |  |  |  |  | 100%
[8 empty] | Optimistic (10%) |  |  | 0
350574.901
Expected (45%)
[8 empty] | 350574.901 |  |  | Contingency %
[8 empty] | Pessimistic (90%) |  |  | 0%
350574.901

## RiskSerializationData (hidden)
3 | 0
0
17.206 | TRUE | 0 | 1 | GF1_rK0qDwEACADNAAwjACYAOABcAGUAZgByAH4AqwApAMcALQD//wAAAAABAQEAAQQAAAAAATAAAAABHkR1cmF0aW9uIC8gQ29uY3JldGUgRm91bmRhdGlvbgEAAQEFAAEAAQMBAQD/AQEBAQEAAQEBAAIAAQEBAQEAAQEBAAIAAYIAAiUAHkR1cmF0aW9uIC8gQ29uY3JldGUgRm91bmRhdGlvbgAALwECAAIAswC9AAEBAgGamZmZmZmpPwAAZmZmZmZm7j8AAAUAAQEBAA== | 1 | 0 | 0 | >75% | <25% | >90% | 17.206 | 42 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
27.206 | TRUE | 0 | 1 | GF1_rK0qDwEACADIAAwjACYAOABaAGMAZABwAHwApwApAMIALQD//wAAAAABAQEAAQQAAAAAATAAAAABHENvbmNyZXRlIGZvdW5kYXRpb24gU2NoZWR1bGUBAAEBBQABAAEDAQEA/wEBAQEBAAEBAQACAAEBAQEBAAEBAQACAAGAAAIjABxDb25jcmV0ZSBmb3VuZGF0aW9uIFNjaGVkdWxlAAAvAQIAAgCvALgAAQECAQAAAAAAAPD/AWZmZmZmZu4/AAAFAAEBAQA= | 1 | 0 | 0 | >75% | <25% | >90% | 27.206 | 44 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
29.6338 | TRUE | 0 | 1 | GF1_rK0qDwEACAC/AAwjACYAOABVAF4AXwBrAHcAnQApALkALQD//wAAAAABAQEAAQQAAAAAATAAAAABF0NsZWFyIHRoZSBzaXRlIFNjaGVkdWxlAQABAQUAAQABAwEBAP8BAQEBAQABAQEAAgABAQEBAQABAQEAAgABewACHgAXQ2xlYXIgdGhlIHNpdGUgU2NoZWR1bGUAAC8BAgACAKUArwABAQIBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQA= | 1 | 0 | 0 | >75% | <25% | >90% | 29.6338 | 49 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 14000 | 6709375 | 36400 | 100
FALSE | 14000 | 6709375 | 36400 | 500
FALSE | 14000 | 6709375 | 36400 | 1000
FALSE | 14000 | 6709375 | 36400 | 1500
FALSE | 14000 | 6709375 | 36400 | 2000
0

## Terminplanung
Nr. | 0 | Duration | 0 | Nr. |  | Duration
Start |  |  |  | Beschreibung
0 | 0 | 0 | 0 | FAZ | GP | FP | FEZ
0 |  |  | 0 | SAZ |  |  | SEZ
Nr. | 0 | Duration | 3 | Nr. | 0 | Duration | 6.8294 |  |  | Nr. | 0 | Duration | 2.4669
BE |  |  |  | Excavation | [5 empty] | Backfill Foundation
0 | 0 | 0 | 3 | 4 | 0 | 0 | 10.8294 |  |  | 27.206 | 0 | 0 | 29.6729
0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | Nr. | 0 | Duration | 17.206 |  |  | Nr. | 0 | Duration | 3
[6 empty] | Concrete foundation | [5 empty] | Rework
[6 empty] | 10 | 0 | 0 | 27.206 |  |  | 22.3125 | 0 | 0 | 25.3125
Simulation | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
Optimistic (10%)
29.6338
expectedic (45%) | [7 empty] | Nr. | 0 | Duration | 6.3125 |  |  | Nr. | 0 | Duration | 3
29.6338 | [7 empty] | Prefabricated columns | [5 empty] | clear the site
Pesimistic (90%) | [7 empty] | 19 | 0 | 0 | 25.3125 |  |  | 26.6338 | 0 | 0 | 29.6338
29.6338 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | Nr. | 0 | Duration | 4.6338 |  |  | Nr. | 0 | Duration | 0
[10 empty] | Brick masonry | [5 empty] | Ende
[10 empty] | 22 | 0 | 0 | 26.6338 |  |  | 29.6338 | 0 | 0 | 29.6338
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[16 empty] | Probability |  |  | 100%
[16 empty] | Expected |  |  | 29.6338

## Calculations
Activity | Quantity | Unit | Performance | Unit | Performance factor | Unit | Duration (hr) | Crew | Duration (Man-hr) | Duration (day) | Expected (45%)
Excavation | 937.5 | m³ | 8.5796 | m³/hr | 0.23311 | Man-hr/m³ | 109.2704 | 2 | 54.6352 | 6.8294 | 6.8294
Blinding lean concrete | 60 | m³
bzw. | 600 | m² | 16.0767 | m²/hr | 0.1244 | Man-hr/m² | 37.321 | 2 | 18.6605 | 2.3326 | 2.3326
Formwork(Foundation) | 452.625 | m²
Concrete (Foundation) | 367.5 | m³ | 0.66746 | m³/hr | 5.9928 | Man-hr/m³ | 550.5914 | 4 | 137.6478 | 17.206 | 17.206
Steel (Foundation) | 29.4 | ton
Concrete Columns | 101 | Piece | 0.5 | Piece /hr | 8 | Man-hr/Piece | 202 | 4 | 50.5 | 6.3125 | 6.3125
Brick masonry | 1300 | m² | 5.8448 | m²/hr | 1.0266 | Man-hr/m² | 222.421 | 6 | 37.0702 | 4.6338 | 4.6338
Backfill | 510 | m³ | 12.921 | m³/hr | 0.15479 | Man-hr/m³ | 39.4708 | 2 | 19.7354 | 2.4669 | 2.4669
Equipment Costs | [7 empty] | Direct Costs | [14 empty] | Direct Costs Overview
Backhoe-loader |  |  |  | Rough-Terrain-Crane |  |  |  | Excavation | [7 empty] | Reinforced Concrete Foundation | [6 empty] | Excavation |  |  |  | Brick masonry
K | = a + v bzw. a + z |  |  | A+V | mean | 4350 |  | Wage | Duration | Unit | Costs | Unit | Total | Unit |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
a | 2.8571 | % |  | BGL | minimum | 4130 |  |  | 54.6352 | Man-hr | 25 | €/Man-hr | 1365.8795 | € |  |  | 137.6478 | Man-hr | 25 | €/Man-hr | 3441.196 | € | Wage | 1365.8795 | 937.5 | 1.4569 | Wage | 926.754 | 1300 | 0.71289
v | 35 | mon |  |  | mean | 4350 |  | Costs. Inv. | Materials | Unit | Engine power | Unit | Diesel | Unit | Total | Costs. Inv. | Quantity | Unit | Costs-Fw. | Unit | Total | Unit | Costs. Inv. | 324.533 | 937.5 | 0.34617 | Costs. Inv. | 31850 | 1300 | 24.5
n | 4 |  |  |  | maximum | 4570 |  |  | 0.12 | l/(Kw*Std) | 60 | KW | 1.1 | €/L | 7.92 | Fromwork | 452.625 | m³ | 8 | €/Man-hr | 3621 | € | Equipment | 2015.6974 | 937.5 | 2.1501 | Equipment
zinz | 6.5 | % |  |  | per Tag | 217.5 |  |  | 0.1 | minimum |  |  | 1 | minimum |  |  |  |  | 7 | minimum |  |  | Sub. Cont. |  |  |  | Sub. Cont.
v | 0.37143 | % |  | Rep BGL | 2830 | €/Month |  |  | 0.12 | mean |  |  | 1.1 | mean |  |  |  |  | 8 | mean |  |  | Total | 3706.1099 |  | 3.9532 | Total | 32776.754 |  | 25.2129
a+v = k | 3.2286 | % |  | Rep Wage | 1698 | €/Month |  |  | 0.15 | maximum |  |  | 1.3 | maximum |  |  |  |  | 10 | maximum |  |  | Probability |  | 100% |  | Probability |  | 100%
NW | 77700 | € |  | Rep Wage SZ | 1748.94 | €/Month |  |  | Total | Unit | hr/day | Workload | Duration (day) | Total | Unit | Total | Quantity | Unit | Costs-Rf.-C. | Unit | Total | Unit | mean (45%) |  | 3706.1099 |  | mean (45%) |  | 32776.754
A+V | 2508.6 | € |  | SZ (%) | mean | 103 |  |  | 7.92 | € | 8 | 75% | 6.8294 | 324.533 | € | Reinforcement | 29.4 | ton | 800 | €/ton | 23520 | $
Per day | 125.43 | €/day |  | SZ (%) | minimum | 101 | [5 empty] | 65% | minimum | [5 empty] | 750 | minimum |  |  | Blinding/lean concrete |  |  |  | Backfill
Per hour | 15.6787 | €/hr |  |  | mean | 103 | [5 empty] | 75% | mean | [5 empty] | 800 | mean |  |  | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
reffektiv | 4.3686 | % |  |  | maximum | 109 | [5 empty] | 85% | maximum | [5 empty] | 1100 | maximum |  |  | Wage | 466.5127 | 600 | 0.77752 | Wage | 493.3845 | 510 | 0.96742
rBGL (%) |  | 2.7 |  | Rep total | 4578.94 | €/Month |  | Equipment | A+V | Unit | Repair | Unit | Duration (day) | Unit | Total | Total | Quantity | Unit | Costs-Conc. | Unit | Total | Unit | Costs. Inv. | 4020 | 600 | 6.7 | Costs. Inv.
| minimum | 2.3 |  | per Tag | 228.947 | €/day |  |  | 125.43 | €/day | 169.7201 | €/At | 6.8294 | Tag | 2015.6974 | Concrete | 367.5 | m³ | 100 | €/m³ | 36750 | $ | Equipment |  |  |  | Equipment
| mean | 2.7 |  | A+V+Rep | 8928.94 | €/Month |  | Total Excavation | [6 empty] | 3706.1099 |  |  |  | 90 | minimum |  |  | Sub. Cont. |  |  |  | Sub. Cont.
| maximum | 4.5 |  | per Tag | 446.447 | €/day | [12 empty] | 100 | mean |  |  | Total | 4486.5127 |  | 7.4775 | Total | 493.3845 |  | 0.96742
SZ | 103 | % | [5 empty] | Blinding | [10 empty] | 115 | maximum |  |  | Probability |  | 100% |  | Probability |  | 100%
R | 3394.4022 | €/Month |  | zu verrechnen |  |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit |  | Total Costs. Inv. | [5 empty] | 63891 | mean (45%) |  | 4486.5127 |  | mean (45%) |  | 493.3845
Per Day | 169.7201 | €/day |  | Duration (day) | Costs (€/AT) | Total (€) |  |  | 18.6605 | Man-hr | 25 | €/Man-hr | 466.5127 | € |  | Total Reinforced Concrete Foundation | [5 empty] | 67332.196
Per Hour | 21.215 | €/hr |  | 27 | 446.447 | 12054.069 |  | Costs. Inv. | Quantity | Unit | Costs | Unit | Total | Unit | [8 empty] | Reinforced Concrete Foundation |  |  |  | Steel structure
A+V+Rep | 5903.0022 | €/Month |  |  | $ per Piece | 119.3472 |  |  | 60 | m³ | 67 | €/Man-hr | 4020 | € |  | Brick masonry | [6 empty] | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
per Tag | 295.1501 | €/day | [8 empty] | 65 | minimum |  |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | Wage | 3441.196 | 367.5 | 9.3638 | Wage
[11 empty] | 67 | mean |  |  |  |  | 37.0702 | Man-hr | 25 | €/Man-hr | 926.754 | € | Costs. Inv. | 63891 | 367.5 | 173.8531 | Costs. Inv.
to settle |  |  |  | Wage | [6 empty] | 72 | maximum |  |  |  | Costs. Inv. | Quantity | Unit | Waste | Costs-masonry | Unit | Total | Equipment |  |  |  | Equipment
Duration (Day) | Costs (€/Day) | Total (€) |  | 25 | €/Man-hr |  |  | Total Blinding/lean concrete | [6 empty] | 4486.5127 | Brick masonry | 1300 | m² | 7.5% | 20 | €/Man-hr | 27950 | Sub. Cont. |  |  |  | Sub. Cont. | 39600 | 24 | 1650
8 | 295.1501 | 2361.2009 | [15 empty] | minimum | 5% | 18 | minimum |  | Total | 67332.196 |  | 183.2169 | Total | 39600 |  | 1650
| $ per m³ | 2.5186 | [5 empty] | Prefabricated Columns | [9 empty] | mean | 7.5% | 20 | mean |  | Probability |  | 100% |  | Probability |  | 100%
[8 empty] | Wage | Duration | Unit | Costs | Unit | Total | Unit |  |  |  | maximum | 10% | 22 | maximum |  | mean (45%) |  | 67332.196 |  | mean (45%) |  | 39600
[9 empty] | 50.5 | Man-hr | 25 | €/Man-hr | 1262.5 | € |  |  | Quantity | Costs-Mort. | Unit | Costs | Unit | Total
[8 empty] | Costs. Inv. | Materials | Unit | Engine power | Unit | Diesel | Unit | Total | Mortar (m³) | 1300 | 0.1 | €/L | 30 | €/m² | 3900 | Prefabricated Columns
[9 empty] | 0.15 | l/(Kw*Std) | 85 | KW | 1.1 | €/L | 14.025 |  |  | 0.08 | minimum | 25 | minimum |  | Cost types | € | Quantity | €/Unit
[9 empty] | 0.13 | minimum |  |  | 1 | minimum |  |  |  | 0.1 | mean | 30 | mean |  | Wage | 1262.5 | 101 | 12.5
[9 empty] | 0.15 | mean |  |  | 1.1 | mean |  |  |  | 0.12 | maximum | 35 | maximum |  | Costs. Inv. | 19971.1969 | 101 | 197.7346
[9 empty] | 0.2 | maximum |  |  | 1.3 | maximum |  | Total Costs. Inv. | [5 empty] | 31850 | Equipment | 2818.1967 | 101 | 27.9029
[9 empty] | Total | Unit | hr/day | Workload | Duration (day) | Total | Unit | Total Brick masonry | [5 empty] | 32776.754 | Sub. Cont.
[9 empty] | 14.025 | € | 8 | 75% | 6.3125 | 531.1969 | € | [7 empty] | Total | 24051.8936 |  | 238.1376
[12 empty] | 65% | minimum |  |  | Backfill | [6 empty] | Probability |  | 100%
[12 empty] | 75% | mean |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | mean (45%) |  | 24051.8936
[12 empty] | 85% | maximum |  |  |  | 19.7354 | Man-hr | 25 | €/Man-hr | 493.3845 | €
[9 empty] | Columns | Quantity | Unit | Costs-Columns | Unit | Total | Unit
[10 empty] | 81 | Piece | 240 | €/Piece | 19440 | € | Steel structure
[12 empty] | 220 | minimum | Costs. Inv. |  | Sub. Cont. | Quantity | Unit | Costs | Unit | Total | Unit
[12 empty] | 240 | mean | 19971.1969 |  |  | 24 | ton | 1650 | €/ton | 39600 | €
[12 empty] | 260 | maximum
[8 empty] | Equipment | A+V | Unit | Repair | Unit | Duration (day) | Unit | Total
[9 empty] | 217.5 | €/day | 228.947 | €/day | 6.3125 | Tag | 2818.1967
[8 empty] | Total Aushub | [6 empty] | 24051.8936
Indirect Costs
| Duration | Unit | Costs | Unit | hr/day | Workload | total
Wage hours | 1500 | Std | 25 | €/hr |  |  | 37500
Supervision | 1.4817 | Mo | 3000 | €/Mo |  |  | 4445.0655
Additional Equipment | 1.4817 | Mo | 3500 | €/Mo |  |  | 5185.9098
Backhoe-loader | 22.8044 | day | 295.1501 | €/day |  |  | 6730.7131
| 29.6338 | day | 7.92 | €/hr | 8 | 75% | 1408.1968
Mobile Crane | 23.3213 | day | 446.447 | €/day |  |  | 10411.7111
| 23.3213 | day | 14.025 | €/hr | 8 | 75% | 1962.4849
Miscellaneous | 1.4817 | Mo | 1000 | €/Mo |  |  | 1481.6885
69125.7696

## Inputs
Considerations to Performance factor |  |  |  |  | Perf. (Wage-hr) | Capacity | Simulation |  |  | NN-Prediction
Aktivität | [6 empty] | Performance |  |  | Activity | [hr/Unit] | Crew | [Unit/hr]
| Performance | Unit | Crew | Unit | [hr/Unit] | [Unit/hr] | Optimistic | Expected | Pessimistic | Excavation | 0.23311 | 2 | 8.5796
Excavation: | 8.5796 | m³/hr | 2 | Man | 0.23311 | 8.5796 | 8.5796 | 8.5796 | 8.5796 | Blinding | 0.1244 | 2 | 16.0767
minimum | 8.408 |  | 1 | minimum |  |  | Crew |  |  | Reinforced Concrete | 0.66746 | 4 | 5.9928
expected | 8.5796 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic | Prefabricated Columns | 8 | 4 | 0.5
maximum | 8.7512 |  | 2 | maximum |  |  | 2 | 2 | 2 | Brick masonry | 1.0266 | 6 | 5.8448
[7 empty] | Aufwand |  |  | Backfill | 0.15479 | 2 | 12.921
[7 empty] | Optimistic | Expected | Pessimistic
Blinding: | 16.0767 | m²/hr | 2 | Mann (LW) | 0.1244 | 16.0767 | 16.0767 | 16.0767 | 16.0767
minimum | 15.7552 |  | 1 | minimum |  |  | Crew
expected | 16.0767 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 16.3983 |  | 2 | maximum |  |  | 2 | 2 | 2
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Reinforced concrete: | 5.9928 | Mann-hr/m³ | 4 | Mann (AW) | 0.66746 | 5.9928 | 5.9928 | 5.9928 | 5.9928
minimum | 5.873 |  | 1 | minimum |  |  | Crew
expected | 5.9928 |  | 4 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 6.1127 |  | 4 | maximum |  |  | 4 | 4 | 4
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Prefabricated reinforced concrete columns: | 8 | Mann-hr/Stk | 4 | Mann (AW) | 8 | 0.5 | 8 | 8 | 8
minimum | 6 |  | 1 | minimum |  |  | Crew
expected | 8 |  | 4 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 10 |  | 4 | maximum |  |  | 4 | 4 | 4
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Brick masonry: | 1.0266 | Mann-hr/m² | 6 | Mann (AW) | 1.0266 | 5.8448 | 1.0266 | 1.0266 | 1.0266
minimum | 1.006 |  | 1 | minimum |  |  | Crew
expected | 1.0266 |  | 6 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 1.0471 |  | 6 | maximum |  |  | 6 | 6 | 6
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Backfill: | 12.921 | m³/hr | 2 | Mann (LW) | 0.15479 | 12.921 | 12.921 | 12.921 | 12.921
minimum | 12.6625 |  | 1 | minimum |  |  | Crew
expected | 12.921 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 13.1794 |  | 2 | maximum |  |  | 2 | 2 | 2

## NN-Predictions
Excavation Numeric | Tag Used | Prediction | Target | Variation
| predict | 0.23311 | 0.23166 | 0.626%
| predict | 0.3207 | 0.32416 | -1.066%
Excavation Text | Tag Used | Prediction | Target | Variation
| predict | 0.29863 | 0.23166 | 28.91%
| predict | 0.30593 | 0.32416 | -5.623%
Blinding Numeric | Tag Used | Prediction | Target | Variation
| predict | 0.12428 | 0.12393 | 0.2804%
| predict | 0.098942 | 0.09792 | 1.044%
Blinding Text | Tag Used | Prediction | Target | Variation
| predict | 0.1244 | 0.12393 | 0.382%
| predict | 0.097958 | 0.09792 | 0.03885%
Reinforced Concrete Numeric | Tag Used | Prediction | Target | Variation
| predict | 0.66781 | 0.66825 | -0.06656%
| predict | 1.5901 | 1.59 | 0.007194%
Reinforced Concrete Text | Tag Used | Prediction | Target | Variation
| predict | 0.66746 | 0.66825 | -0.1176%
| predict | 1.5638 | 1.59 | -1.646%
Masonry Numeric | Tag Used | Prediction | Target | Variation
| predict | 1.0214 | 1.0296 | -0.7965%
| predict | 0.66994 | 0.6669 | 0.4554%
Masonry Text | Tag Used | Prediction | Target | Variation
| predict | 1.0266 | 1.0296 | -0.2954%
| predict | 0.60287 | 0.6669 | -9.601%
Backfil Numeric |  | Prediction | Target | Variation
| predict | 0.10278 | 0.10098 | 1.787%
| predict | 0.15479 | 0.15593 | -0.7297%
Backfil Text | Tag Used | Prediction | Target | Variation
| predict | 0.10277 | 0.10098 | 1.777%
| predict | 0.15472 | 0.15593 | -0.7745%
Note on D2: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Site conditions Equipment Weather Factor
Note on D5: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Site conditions Equipment Weather Independent Numeric Variables: 1 Factor
Note on D9: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Cement Conditions Weather Factor
Note on D12: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Cement Conditions Weather Independent Numeric Variables: 1 Factor
Note on D16: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Concrete Conditions Producer Factor
Note on D19: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Concrete Conditions Producer Independent Numeric Variables: 1 Factor
Note on D23: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Site conditions Equipment Weather Factor
Note on D26: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Site conditions Equipment Weather Independent Numeric Variables: 1 Factor
Note on D30: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 0 Independent Numeric Variables: 5 Crew Site conditions Equipment Weather Factor
Note on D33: NeuralTools Live Prediction Variable Name of Net: "Net Trained on Data Set #1" Net Configuration: GRNN Numeric Predictor Variable Matching: Automatic Independent Category Variables: 4 Crew Site conditions Equipment Weather Independent Numeric Variables: 1 Factor

## Analysis
Alt.- 5.0 m
Criteria | Duration (d) | Expected (45 %) | Pessimistic
Total Duration | 29.6338 | 29.6338 | 29.6338
Excavation | 6.8294 | 6.8294 | 6.8294
Blinding lean concrete | 2.3326 | 2.3326 | 2.3326
Concrete (Foundation) | 17.206 | 17.206 | 17.206
Concrete Columns | 6.3125 | 6.3125 | 6.3125
Brick masonry | 4.6338 | 4.6338 | 4.6338
Backfill | 2.4669 | 2.4669 | 2.4669
Costs | Unit | Probability
Bid Sum (brutto): | 350574.901 | 100%
Contingency (Expected Scenario) | 0
Optimistic Scenario | 350574.901
Expected Scenario | 350574.901
Pessimistic Scenario | 350574.901
Direct Costs | Expected (45%) | Probability
Excavation | 3706.1099 | 100%
Bliding | 4486.5127 | 100%
Prefabricated Columns | 24051.8936 | 100%
Reinforced Conrete Foundation | 67332.196 | 100%
Brick Masonry | 32776.754 | 100%
Backfilling | 493.3845 | 100%