## Example Wall 4.0 m
|  | Kalk-Row: | A | B | C | D | E | F | G | H | J | K | L | M | N | O |  | P | Q | R | S | T | U
[7 empty] | 1. Billing cycle | [10 empty] | 2. Billing cycle
Basic data | [6 empty] | Cost Types with out supplement per unit |  |  |  |  | Cost Types with out supplement Total | [5 empty] | Cost Types with supplement Total |  |  |  | Unit-price | Total-price |  | list of bid items and quantities
Row | Bill of quantities Nr. | Kalk.-Nr. / Short text | Quantity | Unit | Aufwand (Lohn-hr) | Capacity | Wage-Cost | Other-Costs | Equipment-costs | External-costs | Sum Wage-hr | Wage-Cost | Other-Costs | Equipment-costs | External-costs | Kontroll- Summe direct costs |  | Wage-Cost | Other-Costs | Equipment-costs | External-costs
|  |  |  | [Unit] | [hr/Unit] | [Unit/hr] | [€/Unit] | [€/Unit] | [€/Unit] | [€/Unit] | [hr] | [€] | [€] | [€] | [€] | [€] |  | [€] | [€] | [€] | [€] | [€/Unit] | [€]
1 | 1 | Noise and view protection wall | 300 | m | [17 empty] | 894.3265 | 268297.9432
2 | 1.4 | Excavation | 769.5 | m3 | 0.2 | 10 | 1.25 | 0.297 | 1.8447 | 1e-08 | 153.9 | 961.875 | 228.5415 | 1419.4876 | 7.695e-06 | 2609.9041 |  | 6943.0565 | 388.5205 | 1845.3338 | 8.8493e-06 | 11.9258 | 9176.9109 |  | Pos. 1.4
3 | zu 1.3 | Blinding | 600 | m2 | 0.1 | 20 | 0.625 | 6.7 | 1e-08 | 1e-08 | 60 | 375 | 4020 | 6e-06 | 6e-06 | 4395 |  | 2706.8447 | 6834 | 7.8e-06 | 6.9e-06 | 15.9014 | 9540.8447 |  | Pos. 1.3
4 | 1.3 | Reinforced concrete foundation | 270 | m3 | 0.6 | 6.6667 | 10.4167 | 175.6133 | 1e-07 | 1e-07 | 162 | 2812.5 | 47415.6 | 2.7e-05 | 2.7e-05 | 50228.1001 |  | 20301.3349 | 80606.52 | 3.51e-05 | 3.105e-05 | 373.7328 | 100907.855 |  | Pos. 1.3
5 | 1.2 | Prefabricated reinforced concrete columns | 101 | Stk | 8 | 0.5 | 12.5 | 197.7346 | 27.9029 | 1e-08 | 808 | 1262.5 | 19971.1969 | 2818.1967 | 1.01e-06 | 24051.8936 |  | 9113.0437 | 33951.0347 | 3663.6557 | 1.1615e-06 | 462.6508 | 46727.7341 |  | Pos. 1.2
6 | 1.1 | Brick masonry | 1040 | m2 | 1.75 | 3.4286 | 1.2153 | 24.5 | 1e-07 | 1e-07 | 1820 | 1263.8889 | 25480 | 0.000104 | 0.000104 | 26743.8891 |  | 9123.069 | 43316 | 0.0001352 | 0.0001196 | 50.4222 | 52439.0693 |  | Pos. 1.1
7 | zu 1.4 | Backfill | 439.5 | m3 | 0.2 | 10 | 1.25 | 1e-07 | 1e-07 | 1e-07 | 87.9 | 549.375 | 4.395e-05 | 4.395e-05 | 4.395e-05 | 549.3751 |  | 3965.5274 | 7.4715e-05 | 5.7135e-05 | 5.0542e-05 | 9.0228 | 3965.5276 |  | Pos. 1.4
8 | 1.5 | Steel construction | 24 | ton | --- | --- | 1e-05 | 1e-07 | 1e-07 | 1650 | 0.001 | 0.00024 | 2.4e-06 | 2.4e-06 | 39600 | 39600.0002 |  | 0.0017324 | 4.08e-06 | 3.12e-06 | 45540 | 1897.5001 | 45540.0017 |  | Pos. 1.5
9 | [17 empty] | 0 | 0 | 0 | 0
10 | --- | Wages [€/hr] | 25 | [7 empty] | Sum direct costs: | 7225.1391 | 97115.3384 | 4237.6844 | 39600.0002 | 148178.1622 |  | 52152.878 | 165096.0753 | 5508.9898 | 45540.0002 | Kontrolle: | 268297.9432 | = | BS(2)
11 | --- | Sum Direct costs-Wage hours: | 3091.801 | [7 empty] | Sum On-Site overhead: | 42197.9167 | 1565.9722 | 28062.2624 | 1e-05 | 71826.1513 | = | on-site overhead |  | Kontrolle: | 268297.9432
12 | --- | Sum On site overhead-Wage hours | 1500 | [7 empty] | Sum Production costs: | 49423.0558 | 98681.3106 | 32299.9468 | 39600.0002 | 220004.3135 | = | Production costs
13 | --- | Sum Production Costs-Wage hours | 4591.801 | [11 empty] | Indirect Costs | 30854.2635 |  | Wage-Cost | Other-Costs | Equipment-costs | External-costs
14 | --- | Construction time in Weeks: | 12 | [11 empty] | Risk & Profit | 17439.3663 |  | 621.8% | 70% | 30% | 15% | Apportionment in [%]
15 | --- | Average Labour (40 hr/Week): | 9.5663 | [11 empty] | Apportionment of indirect costs: | 120119.7811 | = | 44927.7388 | 67980.7369 | 1271.3053 | 5940 | Apportionment absolut in [$]
16 | --- | Total Indirect costs: | 11.5% | [11 empty] | Total production cost (SK): | 250858.5769 |  |  |  | Kontrolle: | 120119.7811
17 | --- | Risk and Profit: | 6.5% | [11 empty] | Bid Sum (netto): | 268297.9432 | = | BS(1)
18 | --- | Tax rate: | 19% | [11 empty] | Bid Sum (brutto): | 319274.5525
Probability
|  |  | Scenario's confidence interval 10% Optimistic 45% Expected 90% Pessimistic |  |  |  |  | Scenarios |  |  | Contingency |  |  |  |  | 100%
[8 empty] | Optimistic (10%) |  |  | 0
319274.5525
Expected (45%)
[8 empty] | 319274.5525 |  |  | Contingency %
[8 empty] | Pessimistic (90%) |  |  | 0%
319274.5525

## RiskSerializationData (hidden)
3 | 0
0
14.0625 | TRUE | 0 | 1 | GF1_rK0qDwEACADNAAwjACYAOABcAGUAZgByAH4AqwApAMcALQD//wAAAAABAQEAAQQAAAAAATAAAAABHkR1cmF0aW9uIC8gQ29uY3JldGUgRm91bmRhdGlvbgEAAQEFAAEAAQMBAQD/AQEBAQEAAQEBAAIAAQEBAQEAAQEBAAIAAYIAAiUAHkR1cmF0aW9uIC8gQ29uY3JldGUgRm91bmRhdGlvbgAALwECAAIAswC9AAEBAgGamZmZmZmpPwAAZmZmZmZm7j8AAAUAAQEBAA== | 1 | 0 | 0 | >75% | <25% | >90% | 14.0625 | 42 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
24.0625 | TRUE | 0 | 1 | GF1_rK0qDwEACADIAAwjACYAOABaAGMAZABwAHwApwApAMIALQD//wAAAAABAQEAAQQAAAAAATAAAAABHENvbmNyZXRlIGZvdW5kYXRpb24gU2NoZWR1bGUBAAEBBQABAAEDAQEA/wEBAQEBAAEBAQACAAEBAQEBAAEBAQACAAGAAAIjABxDb25jcmV0ZSBmb3VuZGF0aW9uIFNjaGVkdWxlAAAvAQIAAgCvALgAAQECAQAAAAAAAPD/AWZmZmZmZu4/AAAFAAEBAQA= | 1 | 0 | 0 | >75% | <25% | >90% | 24.0625 | 44 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
31.3194 | TRUE | 0 | 1 | GF1_rK0qDwEACAC/AAwjACYAOABVAF4AXwBrAHcAnQApALkALQD//wAAAAABAQEAAQQAAAAAATAAAAABF0NsZWFyIHRoZSBzaXRlIFNjaGVkdWxlAQABAQUAAQABAwEBAP8BAQEBAQABAQEAAgABAQEBAQABAQEAAgABewACHgAXQ2xlYXIgdGhlIHNpdGUgU2NoZWR1bGUAAC8BAgACAKUArwABAQIBmpmZmZmZqT8AAGZmZmZmZu4/AAAFAAEBAQA= | 1 | 0 | 0 | >75% | <25% | >90% | 31.3194 | 49 | 1 | FALSE | TRUE | 0 | FALSE | #NAME?
0
FALSE | 14000 | 6709375 | 36400 | 100
FALSE | 14000 | 6709375 | 36400 | 500
FALSE | 14000 | 6709375 | 36400 | 1000
FALSE | 14000 | 6709375 | 36400 | 1500
FALSE | 14000 | 6709375 | 36400 | 2000
0

## Schedule
Nr. | 0 | Duration | 0 | Nr. |  | Duration
Start |  |  |  | Beschreibung
0 | 0 | 0 | 0 | FAZ | GP | FP | FEZ
0 |  |  | 0 | SAZ |  |  | SEZ
Nr. | 0 | Duration | 3 | Nr. | 0 | Duration | 4.8094 |  |  | Nr. | 0 | Duration | 2.7469
BE |  |  |  | Excavation | [5 empty] | Backfill Foundation
0 | 0 | 0 | 3 | 4 | 0 | 0 | 8.8094 |  |  | 24.0625 | 0 | 0 | 26.8094
0 |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | Nr. | 0 | Duration | 14.0625 |  |  | Nr. | 0 | Duration | 3
[6 empty] | Concrete foundation | [5 empty] | Rework
[6 empty] | 10 | 0 | 0 | 24.0625 |  |  | 22.3125 | 0 | 0 | 25.3125
Simulation | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
Optimistic (10%)
31.3194
expectedic (45%) | [7 empty] | Nr. | 0 | Duration | 6.3125 |  |  | Nr. | 0 | Duration | 3
31.3194 | [7 empty] | Prefabricated columns | [5 empty] | clear the site
Pesimistic (90%) | [7 empty] | 19 | 0 | 0 | 25.3125 |  |  | 28.3194 | 0 | 0 | 31.3194
31.3194 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[10 empty] | Nr. | 0 | Duration | 6.3194 |  |  | Nr. | 0 | Duration | 0
[10 empty] | Brick masonry | [5 empty] | Ende
[10 empty] | 22 | 0 | 0 | 28.3194 |  |  | 31.3194 | 0 | 0 | 31.3194
[10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0
[16 empty] | Probability |  |  | 100%
[16 empty] | Expected |  |  | 31.3194

## Calculations
Activity | Quantity | Unit | Performance | Unit | Performance factor | Unit | Duration (hr) | Crew | Duration (Man-hr) | Duration (day) | Expected (45%)
Excavation | 769.5 | m³ | 10 | m³/hr | 0.2 | Man-hr/m³ | 76.95 | 2 | 38.475 | 4.8094 | 4.8094
Blinding lean concrete | 60 | m³
bzw. | 600 | m² | 20 | m²/hr | 0.1 | Man-hr/m² | 30 | 2 | 15 | 1.875 | 1.875
Formwork(Foundation) | 391.95 | m²
Concrete (Foundation) | 270 | m³ | 0.6 | m³/hr | 6.6667 | Man-hr/m³ | 450 | 4 | 112.5 | 14.0625 | 14.0625
Steel (Foundation) | 21.6 | ton
Concrete Columns | 101 | Piece | 0.5 | Piece /hr | 8 | Man-hr/Piece | 202 | 4 | 50.5 | 6.3125 | 6.3125
Brick masonry | 1040 | m² | 3.4286 | m²/hr | 1.75 | Man-hr/m² | 303.3333 | 6 | 50.5556 | 6.3194 | 6.3194
Backfill | 439.5 | m³ | 10 | m³/hr | 0.2 | Man-hr/m³ | 43.95 | 2 | 21.975 | 2.7469 | 2.7469
Equipment Costs | [7 empty] | Direct Costs | [14 empty] | Direct Costs Overview
Backhoe-loader |  |  |  | Rough-Terrain-Crane |  |  |  | Excavation | [7 empty] | Reinforced Concrete Foundation | [6 empty] | Excavation |  |  |  | Brick masonry
K | = a + v bzw. a + z |  |  | A+V | mean | 4350 |  | Wage | Duration | Unit | Costs | Unit | Total | Unit |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
a | 2.8571 | % |  | BGL | minimum | 4130 |  |  | 38.475 | Man-hr | 25 | €/Man-hr | 961.875 | € |  |  | 112.5 | Man-hr | 25 | €/Man-hr | 2812.5 | € | Wage | 961.875 | 769.5 | 1.25 | Wage | 1263.8889 | 1040 | 1.2153
v | 35 | mon |  |  | mean | 4350 |  | Costs. Inv. | Materials | Unit | Engine power | Unit | Diesel | Unit | Total | Costs. Inv. | Quantity | Unit | Costs-Fw. | Unit | Total | Unit | Costs. Inv. | 228.5415 | 769.5 | 0.297 | Costs. Inv. | 25480 | 1040 | 24.5
n | 4 |  |  |  | maximum | 4570 |  |  | 0.12 | l/(Kw*Std) | 60 | KW | 1.1 | €/L | 7.92 | Fromwork | 391.95 | m³ | 8 | €/Man-hr | 3135.6 | € | Equipment | 1419.4876 | 769.5 | 1.8447 | Equipment
zinz | 6.5 | % |  |  | per Tag | 217.5 |  |  | 0.1 | minimum |  |  | 1 | minimum |  |  |  |  | 7 | minimum |  |  | Sub. Cont. |  |  |  | Sub. Cont.
v | 0.37143 | % |  | Rep BGL | 2830 | €/Month |  |  | 0.12 | mean |  |  | 1.1 | mean |  |  |  |  | 8 | mean |  |  | Total | 2609.9041 |  | 3.3917 | Total | 26743.8889 |  | 25.7153
a+v = k | 3.2286 | % |  | Rep Wage | 1698 | €/Month |  |  | 0.15 | maximum |  |  | 1.3 | maximum |  |  |  |  | 10 | maximum |  |  | Probability |  | 100% |  | Probability |  | 100%
NW | 77700 | € |  | Rep Wage SZ | 1748.94 | €/Month |  |  | Total | Unit | hr/day | Workload | Duration (day) | Total | Unit | Total | Quantity | Unit | Costs-Rf.-C. | Unit | Total | Unit | mean (45%) |  | 2609.9041 |  | mean (45%) |  | 26743.8889
A+V | 2508.6 | € |  | SZ (%) | mean | 103 |  |  | 7.92 | € | 8 | 75% | 4.8094 | 228.5415 | € | Reinforcement | 21.6 | ton | 800 | €/ton | 17280 | $
Per day | 125.43 | €/day |  | SZ (%) | minimum | 101 | [5 empty] | 65% | minimum | [5 empty] | 750 | minimum |  |  | Blinding/lean concrete |  |  |  | Backfill
Per hour | 15.6787 | €/hr |  |  | mean | 103 | [5 empty] | 75% | mean | [5 empty] | 800 | mean |  |  | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
reffektiv | 4.3686 | % |  |  | maximum | 109 | [5 empty] | 85% | maximum | [5 empty] | 1100 | maximum |  |  | Wage | 375 | 600 | 0.625 | Wage | 549.375 | 439.5 | 1.25
rBGL (%) |  | 2.7 |  | Rep total | 4578.94 | €/Month |  | Equipment | A+V | Unit | Repair | Unit | Duration (day) | Unit | Total | Total | Quantity | Unit | Costs-Conc. | Unit | Total | Unit | Costs. Inv. | 4020 | 600 | 6.7 | Costs. Inv.
| minimum | 2.3 |  | per Tag | 228.947 | €/day |  |  | 125.43 | €/day | 169.7201 | €/At | 4.8094 | Tag | 1419.4876 | Concrete | 270 | m³ | 100 | €/m³ | 27000 | $ | Equipment |  |  |  | Equipment
| mean | 2.7 |  | A+V+Rep | 8928.94 | €/Month |  | Total Excavation | [6 empty] | 2609.9041 |  |  |  | 90 | minimum |  |  | Sub. Cont. |  |  |  | Sub. Cont.
| maximum | 4.5 |  | per Tag | 446.447 | €/day | [12 empty] | 100 | mean |  |  | Total | 4395 |  | 7.325 | Total | 549.375 |  | 1.25
SZ | 103 | % | [5 empty] | Blinding | [10 empty] | 115 | maximum |  |  | Probability |  | 100% |  | Probability |  | 100%
R | 3394.4022 | €/Month |  | zu verrechnen |  |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit |  | Total Costs. Inv. | [5 empty] | 47415.6 | mean (45%) |  | 4395 |  | mean (45%) |  | 549.375
Per Day | 169.7201 | €/day |  | Duration (day) | Costs (€/AT) | Total (€) |  |  | 15 | Man-hr | 25 | €/Man-hr | 375 | € |  | Total Reinforced Concrete Foundation | [5 empty] | 50228.1
Per Hour | 21.215 | €/hr |  | 27 | 446.447 | 12054.069 |  | Costs. Inv. | Quantity | Unit | Costs | Unit | Total | Unit | [8 empty] | Reinforced Concrete Foundation |  |  |  | Steel structure
A+V+Rep | 5903.0022 | €/Month |  |  | $ per Piece | 119.3472 |  |  | 60 | m³ | 67 | €/Man-hr | 4020 | € |  | Brick masonry | [6 empty] | Cost types | € | Quantity | €/Unit | Cost types | € | Quantity | €/Unit
per Tag | 295.1501 | €/day | [8 empty] | 65 | minimum |  |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | Wage | 2812.5 | 270 | 10.4167 | Wage
[11 empty] | 67 | mean |  |  |  |  | 50.5556 | Man-hr | 25 | €/Man-hr | 1263.8889 | € | Costs. Inv. | 47415.6 | 270 | 175.6133 | Costs. Inv.
to settle |  |  |  | Wage | [6 empty] | 72 | maximum |  |  |  | Costs. Inv. | Quantity | Unit | Waste | Costs-masonry | Unit | Total | Equipment |  |  |  | Equipment
Duration (Day) | Costs (€/Day) | Total (€) |  | 25 | €/Man-hr |  |  | Total Blinding/lean concrete | [6 empty] | 4395 | Brick masonry | 1040 | m² | 7.5% | 20 | €/Man-hr | 22360 | Sub. Cont. |  |  |  | Sub. Cont. | 39600 | 24 | 1650
8 | 295.1501 | 2361.2009 | [15 empty] | minimum | 5% | 18 | minimum |  | Total | 50228.1 |  | 186.03 | Total | 39600 |  | 1650
| $ per m³ | 3.0685 | [5 empty] | Prefabricated Columns | [9 empty] | mean | 7.5% | 20 | mean |  | Probability |  | 100% |  | Probability |  | 100%
[8 empty] | Wage | Duration | Unit | Costs | Unit | Total | Unit |  |  |  | maximum | 10% | 22 | maximum |  | mean (45%) |  | 50228.1 |  | mean (45%) |  | 39600
[9 empty] | 50.5 | Man-hr | 25 | €/Man-hr | 1262.5 | € |  |  | Quantity | Costs-Mort. | Unit | Costs | Unit | Total
[8 empty] | Costs. Inv. | Materials | Unit | Engine power | Unit | Diesel | Unit | Total | Mortar (m³) | 1040 | 0.1 | €/L | 30 | €/m² | 3120 | Prefabricated Columns
[9 empty] | 0.15 | l/(Kw*Std) | 85 | KW | 1.1 | €/L | 14.025 |  |  | 0.08 | minimum | 25 | minimum |  | Cost types | € | Quantity | €/Unit
[9 empty] | 0.13 | minimum |  |  | 1 | minimum |  |  |  | 0.1 | mean | 30 | mean |  | Wage | 1262.5 | 101 | 12.5
[9 empty] | 0.15 | mean |  |  | 1.1 | mean |  |  |  | 0.12 | maximum | 35 | maximum |  | Costs. Inv. | 19971.1969 | 101 | 197.7346
[9 empty] | 0.2 | maximum |  |  | 1.3 | maximum |  | Total Costs. Inv. | [5 empty] | 25480 | Equipment | 2818.1967 | 101 | 27.9029
[9 empty] | Total | Unit | hr/day | Workload | Duration (day) | Total | Unit | Total Brick masonry | [5 empty] | 26743.8889 | Sub. Cont.
[9 empty] | 14.025 | € | 8 | 75% | 6.3125 | 531.1969 | € | [7 empty] | Total | 24051.8936 |  | 238.1376
[12 empty] | 65% | minimum |  |  | Backfill | [6 empty] | Probability |  | 100%
[12 empty] | 75% | mean |  |  | Wage | Duration | Unit | Costs | Unit | Total | Unit | mean (45%) |  | 24051.8936
[12 empty] | 85% | maximum |  |  |  | 21.975 | Man-hr | 25 | €/Man-hr | 549.375 | €
[9 empty] | Columns | Quantity | Unit | Costs-Columns | Unit | Total | Unit
[10 empty] | 81 | Piece | 240 | €/Piece | 19440 | € | Steel structure
[12 empty] | 220 | minimum | Costs. Inv. |  | Sub. Cont. | Quantity | Unit | Costs | Unit | Total | Unit
[12 empty] | 240 | mean | 19971.1969 |  |  | 24 | ton | 1650 | €/ton | 39600 | €
[12 empty] | 260 | maximum
[8 empty] | Equipment | A+V | Unit | Repair | Unit | Duration (day) | Unit | Total
[9 empty] | 217.5 | €/day | 228.947 | €/day | 6.3125 | Tag | 2818.1967
[8 empty] | Total Aushub | [6 empty] | 24051.8936
Indirect Costs
| Duration | Unit | Costs | Unit | hr/day | Workload | total
Wage hours | 1500 | Std | 25 | €/hr |  |  | 37500
Supervision | 1.566 | Mo | 3000 | €/Mo |  |  | 4697.9167
Additional Equipment | 1.566 | Mo | 3500 | €/Mo |  |  | 5480.9028
Backhoe-loader | 26.5101 | day | 295.1501 | €/day |  |  | 7824.4499
| 31.3194 | day | 7.92 | €/hr | 8 | 75% | 1488.3
Mobile Crane | 25.0069 | day | 446.447 | €/day |  |  | 11164.2753
| 25.0069 | day | 14.025 | €/hr | 8 | 75% | 2104.3344
Miscellaneous | 1.566 | Mo | 1000 | €/Mo |  |  | 1565.9722
71826.1513

## Inputs
Considerations to Performance factor |  |  |  |  | Perf. (Wage-hr) | Capacity | Simulation |  |  | NN-Prediction
Aktivität | [6 empty] | Performance |  |  | Activity | [hr/Unit] | Crew | [Unit/hr]
| Performance | Unit | Crew | Unit | [hr/Unit] | [Unit/hr] | Optimistic | Expected | Pessimistic | Excavation | 0.2 | 2 | 10
Excavation: | 10 | m³/hr | 2 | Man | 0.2 | 10 | 10 | 10 | 10 | Blinding | 0.1 | 2 | 20
minimum | 7.5 |  | 1 | minimum |  |  | Crew |  |  | Reinforced Concrete | 0.6 | 4 | 6.6667
expected | 10 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic | Prefabricated Columns | 8 | 4 | 0.5
maximum | 12 |  | 2 | maximum |  |  | 2 | 2 | 2 | Brick masonry | 1.75 | 6 | 3.4286
[7 empty] | Aufwand |  |  | Backfill | 0.2 | 2 | 10
[7 empty] | Optimistic | Expected | Pessimistic
Blinding: | 20 | m²/hr | 2 | Mann (LW) | 0.1 | 20 | 20 | 20 | 20
minimum | 15 |  | 1 | minimum |  |  | Crew
expected | 20 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 22 |  | 2 | maximum |  |  | 2 | 2 | 2
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Reinforced concrete: | 6.6667 | Mann-hr/m³ | 4 | Mann (AW) | 0.6 | 6.6667 | 6.6667 | 6.6667 | 6.6667
minimum | 3 |  | 1 | minimum |  |  | Crew
expected | 6.6667 |  | 4 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 8 |  | 4 | maximum |  |  | 4 | 4 | 4
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Prefabricated reinforced concrete columns: | 8 | Mann-hr/Stk | 4 | Mann (AW) | 8 | 0.5 | 8 | 8 | 8
minimum | 6 |  | 1 | minimum |  |  | Crew
expected | 8 |  | 4 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 10 |  | 4 | maximum |  |  | 4 | 4 | 4
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Brick masonry: | 1.75 | Mann-hr/m² | 6 | Mann (AW) | 1.75 | 3.4286 | 1.75 | 1.75 | 1.75
minimum | 1.2 |  | 1 | minimum |  |  | Crew
expected | 1.75 |  | 6 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 2 |  | 6 | maximum |  |  | 6 | 6 | 6
Aufwand
[7 empty] | Optimistic | Expected | Pessimistic
Backfill: | 10 | m³/hr | 2 | Mann (LW) | 0.2 | 10 | 10 | 10 | 10
minimum | 9 |  | 1 | minimum |  |  | Crew
expected | 10 |  | 2 | expected |  |  | Optimistic | Expected | Pessimistic
maximum | 13 |  | 2 | maximum |  |  | 2 | 2 | 2

## Analysis
Alt.- 4.0 m
Criteria | Duration (d) | Expected (45 %) | Pessimistic
Total Duration | 31.3194 | 31.3194 | 31.3194
Excavation | 4.8094 | 4.8094 | 4.8094
Blinding lean concrete | 1.875 | 1.875 | 1.875
Concrete (Foundation) | 14.0625 | 14.0625 | 14.0625
Concrete Columns | 6.3125 | 6.3125 | 6.3125
Brick masonry | 6.3194 | 6.3194 | 6.3194
Backfill | 2.7469 | 2.7469 | 2.7469
Costs | Unit | Probability
Bid Sum (brutto): | 319274.5525 | 100%
Contingency (Expected Scenario) | 0
Optimistic Scenario | 319274.5525
Expected Scenario | 319274.5525
Pessimistic Scenario | 319274.5525
Direct Costs | Expected (45%) | Probability
Excavation | 2609.9041 | 100%
Bliding | 4395 | 100%
Prefabricated Columns | 24051.8936 | 100%
Reinforced Conrete Foundation | 50228.1 | 100%
Brick Masonry | 26743.8889 | 100%
Backfilling | 549.375 | 100%